## Vplan
Total Items | 622
Pass Items | 622
Fail Items | 0
NY Items | 0
Section | Main Title | Description | Testname | Priority | Method | Owner | Status | Milestone | Remark
1 | Register test
1.1 | Default value + read/write | 1. Config the attributes of the registers in UVM_RAL regmodel following spec. 2. Start 2 built-in sequence in test: uvm_reg_hw_reset_seq, uvm_reg_bit_bash_seq. Pass condititon: Registers operation are valid. | uart_reg_scan_test | High | Directed and checker | Loc | P | June .20
1.2 | Write 1 to clear FSR.parity_error_status (FSR[4]) | 1. IER[4] = 0 2. Config UART IP receive 8 data bits with even parity, VIP send 8 data bits with odd parity. 3. Ensure parity_error trigger event. 4. Wait UART IP received completely. 5. Read FSR 6. Write 0 into FSR[4], read FSR[4]. 7. Write 1 into FSR[4], read FSR[4] Pass condition: FSR[4] = 1 in step 6, FSR[4] = 0 in step 7 | parity_error_w1c | High | Directed and checker | Loc | P | July.09
2 | Oversampling | [6 empty] | June.30
2.1 | 16x - Baudrate | 1.Config UART IP operate with x16 oversampling following the baudrate below 2.Config VIP(validated before) operate at the same baudrate as UART IP, with full_duplex mode, no parity. 3. Both sides transmit and receive two data bytes. Pass condittion: Both sides transmit and receive the correct data and baudrate.
2.1.1 | _2400 | same as above | x16_2400 | High | Directed and checker | Loc | P
2.1.2 | _4800 | same as above | x16_4800 | High | Directed and checker | Loc | P
2.1.3 | _9600 | same as above | x16_9600 | High | Directed and checker | Loc | P
2.1.4 | _19200 | same as above | x16_19200 | High | Directed and checker | Loc | P
2.1.5 | _38400 | same as above | x16_38400 | High | Directed and checker | Loc | P
2.1.6 | _76800 | same as above | x16_76800 | High | Directed and checker | Loc | P
2.1.7 | _115200 | same as above | x16_115200 | High | Directed and checker | Loc | P
2.1.8 | _Custom_230400 | same as above with custom baudrate 230400 | x16_230400 | High | Directed and checker | Loc | P
2.2 | 13x - Baudrate | 1.Config UART IP operate with x13 oversampling following the baudrate below 2.Config VIP(validated before) operate at the same baudrate as UART IP, with full_duplex mode, no parity. 3. Both sides transmit and receive two data bytes. Pass condittion: Both sides transmit and receive the correct data and baudrate.
2.2.1 | _2400 | same as above | x13_2400 | High | Directed and checker | Loc | P
2.2.2 | _4800 | same as above | x13_4800 | High | Directed and checker | Loc | P
2.2.3 | _9600 | same as above | x13_9600 | High | Directed and checker | Loc | P
2.2.4 | _19200 | same as above | x13_19200 | High | Directed and checker | Loc | P
2.2.5 | _38400 | same as above | x13_38400 | High | Directed and checker | Loc | P
2.2.6 | _76800 | same as above | x13_76800 | High | Directed and checker | Loc | P
2.2.7 | _115200 | same as above | x13_115200 | High | Directed and checker | Loc | P
2.1.8 | _Custom_230400 | same as above | x13_230400 | High | Directed and checker | Loc | P
same as above with custom baudrate 230400
3 | Half-duplex_transmit only | [6 empty] | July.02
All baudrates combine with the below, randomize oversampling
data_bits x parity x stop_bits
3.1 | 5_no_1 | same as above | tx_2400_5_no_1 | High | Directed and checker | Loc
3.2 | 6_no_1 | same as above | tx_2400_6_no_1 | Medium | Directed and checker | Loc
3.3 | 7_no_1 | same as above | tx_2400_7_no_1 | Medium | Directed and checker | Loc
3.4 | 8_no_1 | same as above | tx_2400_8_no_1 | Medium | Directed and checker | Loc
3.5 | 5_even_1 | same as above | tx_2400_5_even_1 | High | Directed and checker | Loc
3.6 | 6_even_1 | same as above | tx_2400_6_even_1 | Medium | Directed and checker | Loc
3.7 | 7_even_1 | same as above | tx_2400_7_even_1 | Medium | Directed and checker | Loc
3.8 | 8_even_1 | same as above | tx_2400_8_even_1 | Medium | Directed and checker | Loc
3.9 | 5_odd_1 | same as above | tx_2400_5_odd_1 | High | Directed and checker | Loc
3.1X | 6_odd_1 | same as above | tx_2400_6_odd_1 | Medium | Directed and checker | Loc
3.11 | 7_odd_1 | same as above | tx_2400_7_odd_1 | Medium | Directed and checker | Loc
3.12 | 8_odd_1 | same as above | tx_2400_8_odd_1 | Medium | Directed and checker | Loc
3.13 | 5_no_2 | same as above | tx_2400_5_no_2 | High | Directed and checker | Loc
3.14 | 6_no_2 | same as above | tx_2400_6_no_2 | Medium | Directed and checker | Loc
3.15 | 7_no_2 | same as above | tx_2400_7_no_2 | Medium | Directed and checker | Loc
3.16 | 8_no_2 | same as above | tx_2400_8_no_2 | Medium | Directed and checker | Loc
3.17 | 5_even_2 | same as above | tx_2400_5_even_2 | High | Directed and checker | Loc
3.18 | 6_even_2 | same as above | tx_2400_6_even_2 | Medium | Directed and checker | Loc
3.19 | 7_even_2 | same as above | tx_2400_7_even_2 | Medium | Directed and checker | Loc
3.2X | 8_even_2 | same as above | tx_2400_8_even_2 | Medium | Directed and checker | Loc
3.21 | 5_odd_2 | same as above | tx_2400_5_odd_2 | High | Directed and checker | Loc
3.22 | 6_odd_2 | same as above | tx_2400_6_odd_2 | Medium | Directed and checker | Loc
3.23 | 7_odd_2 | same as above | tx_2400_7_odd_2 | Medium | Directed and checker | Loc
3.24 | 8_odd_2 | same as above | tx_2400_8_odd_2 | Medium | Directed and checker | Loc
…
4 | Half-duplex_receive only | [6 empty] | July.02
same as item 3
5 | Full-duplex | [6 empty] | July.02
same as item 3
6 | Interupt | [6 empty] | July.03
6.1 | parity_error_en | 1. Config IER[4] = 1. 2. Config UART IP receive 8 data bits with even parity, VIP send 8 data bits with odd parity. 3. Capture time event of parity bit error. Pass condition: Interrupt signal asserted after event trigger - | parity_error_en | High | Directed and checker | Loc | P |  | Using error_catcher to demote error messages: "Parity mismatch" ensures that the test passes
6.2 | parity_error_dis | 1. Config IER[4] = 0. 2. Config UART IP receive 8 data bits with even parity, VIP send 8 data bits with odd parity. 3. Wait UART IP received completely. Pass condition: FSR[4] = 1 and Interrupt signal deasserted | parity_error_dis | High | Directed and checker | Loc | P |  | Using error_catcher to demote error messages: "Parity mismatch" ensures that the test passes
6.3 | tx_fifo_empty_en | 1. Config IER[1] = 1. 2. Config to transmit continuously 2 data bytes from UART IP to VIP 3. Capture the end time of the first transmitted byte. (event trigger) 4. Observe Interrupt signal during sim Pass condition: Interrupt signal asserted after event trigger - VIP received completely and exactly data bytes. | tx_fifo_empty_en | High | Directed and checker | Loc | P
6.4 | tx_fifo_empty_dis | 1. Config IER[1] = 0. 2. Config to transmit continuously 2 data bytes from UART IP to VIP 3. Wait VIP received completely data 5. Read data out from FSR 4. Observe Interrupt signal during sim Pass condition: FSR[1] = 1 and Interrupt signal is deassert during sim - VIP received complete and exactly data bytes. | tx_fifo_empty_dis | High | Directed and checker | Loc | P
6.5 | tx_fifo_full_en | 1. Config IER[0] = 1. 2. Config LCR.BGE = 0 to disable generate baudrate 3. Write continuously 17 data bytes into TBR so that 17th byte is different from previous bytes 4. Capture event time of the 17th data is written into TBR 5. Observe Interrupt signal during sim Pass condition: Interrupt signal is asserted after event trigger | tx_fifo_full_en | High | Directed and checker | Loc | P
6.6 | tx_fifo_full_dis | 1. Config IER[0] = 0 2. Config LCR.BGE = 0 to disable generate baudrate. 3. Write continuously 17 data bytes into TBR so that 17th byte is different from previous bytes 4. Then, read data out from FSR 5. Observe Interrupt signal during sim Pass condition: FSR[0] = 1 - Interrupt signal is always deasserted | tx_fifo_full_dis | High | Directed and checker | Loc | P
6.7 | rx_fifo_empty_en | 1. Config IER[3] = 1. 2. Config to transmit continuously 2 data bytes from VIP to UART VIP 3. Read all data out from RBR 4. Wait step 3 done, capture the event time when all data has been read from the RBR. 5. Observe Interrupt signal during sim. Pass condition: Interrupt is asserted after event trigger - UART IP received completely and exactly data. | rx_fifo_empty_en | High | Directed and checker | Loc | P
6.8 | rx_fifo_empty_dis | 1. Config IER[3] = 0. 2. Config to transmit continuously 2 data bytes from VIP to UART VIP 3. Read all data out from RBR. 4. Wait step 3 done, read data out from FSR. 5. Observe Interrupt signal during sim. Pass condition: FSR[3] = 1 and Interrupt is always deasserted during sim - UART IP received completely and exactly data. | rx_fifo_empty_dis | High | Directed and checker | Loc | P
6.9 | rx_fifo_full_en | 1. Config IER[2] = 1. 2. Config to transmit continuously 17 data bytes from VIP to UART VIP 3. Capture event time when VIP transmited completely 17th data byte.(event trigger) 4. Observe Interrupt signal during sim. Pass condition: Interrupt is asserted after event trigger - UART IP received completely and exactly data. | rx_fifo_full_en | High | Directed and checker | Loc | P
6.10x | rx_fifo_full_dis | 1. Config IER[2] = 0. 2. Config to transmit continuously 17 data bytes from VIP to UART VIP. 3. Wait step 2 done, read data out from FSR. 4. Observe Interrupt signal during sim. Pass condition: FSR[2] = 1 - Interrupt is always deasserted during sim - UART IP received completely and exactly data. | rx_fifo_full_dis | High | Directed and checker | Loc | P
7 | Error injection | Full-duplex mode x16 | [5 empty] | July.03
7.1 | Data bits mismatch | 1. UART IP and VIP is different at data bits: UART IP data bits = 5, VIP data bits = 8 2. Config other parameters so that VIP and UART IP have the same configuration Pass condition: UART IP transmit data frame is different from VIP receive data frame, VIP transmit data frame is different from UART VIP receive data frame. | data_bits_mismatch | High | Directed and checker | Loc | P |  | Using error_catcher to demote error messages ensures that the test passes
7.2 | Baudrate mismatch | 1. UART IP and VIP is different at data bits: UART IP baudrate = 115200, VIP data bits = 76800 2. Config other parameters so that VIP and UART IP have the same configuration Pass condition: UART IP transmit data frame is different from VIP receive data frame, VIP transmit data frame is different from UART VIP receive data frame. | baudrate_mismatch | High | Directed and checker | Loc | P |  | Using error_catcher to demote error messages ensures that the test passes
7.3 | Parity mismatch | 1. UART IP and VIP is different at parity mode: UART IP uses parity, VIP don't use parity (no parity) 2. Config other parameters so that UART IP and IP have the same configuration 3. Send data frame continuously Pass condition: UART IP transmit data frame is different from VIP receive data frame, VIP transmit data frame is different from UART IP receive data frame. | parity_mismatch | High | Directed and checker | Loc | P |  | Using error_catcher to demote error messages ensures that the test passes
7.4 | Stop bits mismatch | 1. UART IP and VIP is different at parity mode: UART IP stop bits = 2, VIP stop bits = 1 2. Config other parameters so that UART IP and IP have the same configuration 3. Send data frame continuously Pass condition: UART IP transmit data frame is different from VIP receive data frame, VIP transmit data frame is different from UART IP receive data frame. | stop_bits_mismatch | High | Directed and checker | Loc | P |  | Using error_catcher to demote error messages ensures that the test passes
8 | Error handling | [6 empty] | July.04
8.1 | Access_rsvd | 1. Write randomly a data byte so that it is not 32'hFFFF_FFFF to the address in range [0x020: 0x3FF] 2. Read out from address 32'hFFFF_FFFF 3. Compare data in and data out 4. Observe HRESP singnal during simulation 5. Capture the event time of read/write read transaction and posedge of HRESP Pass condition: - Data out is 32'hFFFF_FFFF, diferrent from data in. - HRESP asserted after event trigger | access_rsvd | High | Directed and checker | Loc | P
8.2 | Write data when TX FIFO is full | 1. Config LCR.BGE = 0 to disable generate baudrate. 2. Write continuously 17 data bytes into TBR so that 17th byte is different from previous bytes 3. Config LCR to start transmission. Pass condition: VIP ignored 17th byte and received exactly previous 16 bytes | write_tx_fifo_full | High | Directed and checker | Loc | P
9 | Dynamic reconfig | [6 empty] | July.04
Transmit only
9.1 | Reconfig baudrate | 1. Config UART IP and VIP operate with baudrate 76800 2. Run half-duplex mode to UART IP transmit 2 bytes data continuously 3. Wait step 2 done, Reconfig baudrate UART IP and VIP operate with baudrate 115200. 4.Transmit new 2 bytes data and received 2 bytes data continuously Pass condition: UART IP and VIP applied new baudrate 115200 and transmit and receive fully data bytes | tx_baudrate_reconfig | High | Directed and checker | Loc | P
9.2 | Reconfig data bits | 1. Config UART IP and VIP operate with 7 data bits 2. Run half-duplex mode to UART IP transmit 2 bytes data continuously 3. Wait step 2 done, Reconfig UART IP and VIP operate with 8 data bits. 4.Transmit new 2 bytes data and received 2 bytes data continuosly continuously Pass condition: UART IP and VIP applied new data bits and transmit and receive fully data bytes | tx_data_bits_ reconfig | High | Directed and checker | Loc | P
9.3 | Reconfig parity mode | 1. Config UART IP and VIP operate without parity 2. Run half-duplex mode to UART IP transmit 2 bytes data continuously 3. Wait step 2 done, Reconfig UART IP and VIP operate with parity 4.Transmit new 2 bytes data and received 2 bytes data continuously Pass condition: UART IP and VIP applied new parity mode and transmit and receive fully data bytes | tx_parity_reconfig | High | Directed and checker | Loc | P
9.4 | Reconfig stop bits | 1. Config UART IP and VIP operate with 1 stop bits 2. Run half-duplex mode to UART IP transmit 2 bytes data continuously 3. Wait step 2 done, Reconfig UART IP and VIP operate with 2 stop bits 4.Transmit new 2 bytes data and received 2 bytes data continuously Pass condition: UART IP and VIP applied new stop bits and transmit and receive fully data bytes | tx_stop_bits_reconfig | High | Directed and checker | Loc | P
Receive obly
9.5 | Reconfig baudrate | 1. Config UART IP and VIP operate with baudrate 76800 2. Run half-duplex mode to UART IP receive 2 bytes data continuously 3. Wait step 2 done, Reconfig baudrate UART IP and VIP operate with baudrate 115200. 4.Transmit new 2 bytes data and received 2 bytes data continuously Pass condition: UART IP and VIP applied new baudrate 115200 and transmit and receive fully data bytes | rx_baudrate_reconfig | High | Directed and checker | Loc | P
9.6 | Reconfig data bits | 1. Config UART IP and VIP operate with 7 data bits 2. Run half-duplex mode to UART IP receive 2 bytes data continuously 3. Wait step 2 done, Reconfig UART IP and VIP operate with 8 data bits. 4.Transmit new 2 bytes data and received 2 bytes data continuosly continuously Pass condition: UART IP and VIP applied new data bits and transmit and receive fully data bytes | rx_data_bits_ reconfig | High | Directed and checker | Loc | P
9.7 | Reconfig parity mode | 1. Config UART IP and VIP operate without parity 2. Run half-duplex mode to UART IP receive 2 bytes data continuously 3. Wait step 2 done, Reconfig UART IP and VIP operate with parity 4.Transmit new 2 bytes data and received 2 bytes data continuously Pass condition: UART IP and VIP applied new parity mode and transmit and receive fully data bytes | rx_parity_reconfig | High | Directed and checker | Loc | P
9.8 | Reconfig stop bits | 1. Config UART IP and VIP operate with 2 stop bits 2. Run half-duplex mode to UART IP receive 2 bytes data continuously 3. Wait step 2 done, Reconfig UART IP and VIP operate with 1 stop bits 4.Transmit new 2 bytes data and received 2 bytes data continuously Pass condition: UART IP and VIP applied new stop bits and transmit and receive fully data bytes | rx_stop_bits_reconfig | High | Directed and checker | Loc | P
Full-duplex
9.9 | Reconfig baudrate | 1. Config UART IP and VIP operate with baudrate 76800 2. Run full-duplex mode to transmit 2 bytes data and received 2 bytes data continuously 3. Wait step 2 done, Reconfig baudrate UART IP and VIP operate with baudrate 115200. 4.Transmit new 2 bytes data and received 2 bytes data continuously Pass condition: UART IP and VIP applied new baudrate 115200 and transmit and receive fully data bytes | full_baudrate_reconfig | High | Directed and checker | Loc | P
9.x | Reconfig data bits | 1. Config UART IP and VIP operate with 7 data bits 2. Run full-duplex mode to transmit 2 bytes data and received 2 bytes data continuously 3. Wait step 2 done, Reconfig UART IP and VIP operate with 8 data bits. 4.Transmit new 2 bytes data and received 2 bytes data continuosly continuously Pass condition: UART IP and VIP applied new data bits and transmit and receive fully data bytes | full_data_bits_ reconfig | High | Directed and checker | Loc | P
9.11 | Reconfig parity mode | 1. Config UART IP and VIP operate without parity 2. Run full-duplex mode to transmit 2 bytes data and received 2 bytes data continuously 3. Wait step 2 done, Reconfig UART IP and VIP operate with parity 4.Transmit new 2 bytes data and received 2 bytes data continuously Pass condition: UART IP and VIP applied new parity mode and transmit and receive fully data bytes | full_parity_reconfig | High | Directed and checker | Loc | P
9.12 | Reconfig stop bits | 1. Config UART IP and VIP operate with 1 stop bits 2. Run full-duplex mode to transmit 2 bytes data and received 2 bytes data continuously 3. Wait step 2 done, Reconfig UART IP and VIP operate with 2 stop bits 4.Transmit new 2 bytes data and received 2 bytes data continuously Pass condition: UART IP and VIP applied new stop bits and transmit and receive fully data bytes | full_stop_bits_reconfig | High | Directed and checker | Loc | P

## transmitter_test
Testname | Status | Remark
tx_2400_5_no_1 | P
tx_2400_6_no_1 | P
tx_2400_7_no_1 | P
tx_2400_8_no_1 | P
tx_2400_5_even_1 | P
tx_2400_6_even_1 | P
tx_2400_7_even_1 | P
tx_2400_8_even_1 | P
tx_2400_5_odd_1 | P
tx_2400_6_odd_1 | P
tx_2400_7_odd_1 | P
tx_2400_8_odd_1 | P
tx_2400_5_no_2 | P
tx_2400_6_no_2 | P
tx_2400_7_no_2 | P
tx_2400_8_no_2 | P
tx_2400_5_even_2 | P
tx_2400_6_even_2 | P
tx_2400_7_even_2 | P
tx_2400_8_even_2 | P
tx_2400_5_odd_2 | P
tx_2400_6_odd_2 | P
tx_2400_7_odd_2 | P
tx_2400_8_odd_2 | P
tx_4800_5_no_1 | P
tx_4800_6_no_1 | P
tx_4800_7_no_1 | P
tx_4800_8_no_1 | P
tx_4800_5_even_1 | P
tx_4800_6_even_1 | P
tx_4800_7_even_1 | P
tx_4800_8_even_1 | P
tx_4800_5_odd_1 | P
tx_4800_6_odd_1 | P
tx_4800_7_odd_1 | P
tx_4800_8_odd_1 | P
tx_4800_5_no_2 | P
tx_4800_6_no_2 | P
tx_4800_7_no_2 | P
tx_4800_8_no_2 | P
tx_4800_5_even_2 | P
tx_4800_6_even_2 | P
tx_4800_7_even_2 | P
tx_4800_8_even_2 | P
tx_4800_5_odd_2 | P
tx_4800_6_odd_2 | P
tx_4800_7_odd_2 | P
tx_4800_8_odd_2 | P
tx_9600_5_no_1 | P
tx_9600_6_no_1 | P
tx_9600_7_no_1 | P
tx_9600_8_no_1 | P
tx_9600_5_even_1 | P
tx_9600_6_even_1 | P
tx_9600_7_even_1 | P
tx_9600_8_even_1 | P
tx_9600_5_odd_1 | P
tx_9600_6_odd_1 | P
tx_9600_7_odd_1 | P
tx_9600_8_odd_1 | P
tx_9600_5_no_2 | P
tx_9600_6_no_2 | P
tx_9600_7_no_2 | P
tx_9600_8_no_2 | P
tx_9600_5_even_2 | P
tx_9600_6_even_2 | P
tx_9600_7_even_2 | P
tx_9600_8_even_2 | P
tx_9600_5_odd_2 | P
tx_9600_6_odd_2 | P
tx_9600_7_odd_2 | P
tx_9600_8_odd_2 | P
tx_19200_5_no_1 | P
tx_19200_6_no_1 | P
tx_19200_7_no_1 | P
tx_19200_8_no_1 | P
tx_19200_5_even_1 | P
tx_19200_6_even_1 | P
tx_19200_7_even_1 | P
tx_19200_8_even_1 | P
tx_19200_5_odd_1 | P
tx_19200_6_odd_1 | P
tx_19200_7_odd_1 | P
tx_19200_8_odd_1 | P
tx_19200_5_no_2 | P
tx_19200_6_no_2 | P
tx_19200_7_no_2 | P
tx_19200_8_no_2 | P
tx_19200_5_even_2 | P
tx_19200_6_even_2 | P
tx_19200_7_even_2 | P
tx_19200_8_even_2 | P
tx_19200_5_odd_2 | P
tx_19200_6_odd_2 | P
tx_19200_7_odd_2 | P
tx_19200_8_odd_2 | P
tx_38400_5_no_1 | P
tx_38400_6_no_1 | P
tx_38400_7_no_1 | P
tx_38400_8_no_1 | P
tx_38400_5_even_1 | P
tx_38400_6_even_1 | P
tx_38400_7_even_1 | P
tx_38400_8_even_1 | P
tx_38400_5_odd_1 | P
tx_38400_6_odd_1 | P
tx_38400_7_odd_1 | P
tx_38400_8_odd_1 | P
tx_38400_5_no_2 | P
tx_38400_6_no_2 | P
tx_38400_7_no_2 | P
tx_38400_8_no_2 | P
tx_38400_5_even_2 | P
tx_38400_6_even_2 | P
tx_38400_7_even_2 | P
tx_38400_8_even_2 | P
tx_38400_5_odd_2 | P
tx_38400_6_odd_2 | P
tx_38400_7_odd_2 | P
tx_38400_8_odd_2 | P
tx_76800_5_no_1 | P
tx_76800_6_no_1 | P
tx_76800_7_no_1 | P
tx_76800_8_no_1 | P
tx_76800_5_even_1 | P
tx_76800_6_even_1 | P
tx_76800_7_even_1 | P
tx_76800_8_even_1 | P
tx_76800_5_odd_1 | P
tx_76800_6_odd_1 | P
tx_76800_7_odd_1 | P
tx_76800_8_odd_1 | P
tx_76800_5_no_2 | P
tx_76800_6_no_2 | P
tx_76800_7_no_2 | P
tx_76800_8_no_2 | P
tx_76800_5_even_2 | P
tx_76800_6_even_2 | P
tx_76800_7_even_2 | P
tx_76800_8_even_2 | P
tx_76800_5_odd_2 | P
tx_76800_6_odd_2 | P
tx_76800_7_odd_2 | P
tx_76800_8_odd_2 | P
tx_115200_5_no_1 | P
tx_115200_6_no_1 | P
tx_115200_7_no_1 | P
tx_115200_8_no_1 | P
tx_115200_5_even_1 | P
tx_115200_6_even_1 | P
tx_115200_7_even_1 | P
tx_115200_8_even_1 | P
tx_115200_5_odd_1 | P
tx_115200_6_odd_1 | P
tx_115200_7_odd_1 | P
tx_115200_8_odd_1 | P
tx_115200_5_no_2 | P
tx_115200_6_no_2 | P
tx_115200_7_no_2 | P
tx_115200_8_no_2 | P
tx_115200_5_even_2 | P
tx_115200_6_even_2 | P
tx_115200_7_even_2 | P
tx_115200_8_even_2 | P
tx_115200_5_odd_2 | P
tx_115200_6_odd_2 | P
tx_115200_7_odd_2 | P
tx_115200_8_odd_2 | P
tx_230400_5_no_1 | P
tx_230400_6_no_1 | P
tx_230400_7_no_1 | P
tx_230400_8_no_1 | P
tx_230400_5_even_1 | P
tx_230400_6_even_1 | P
tx_230400_7_even_1 | P
tx_230400_8_even_1 | P
tx_230400_5_odd_1 | P
tx_230400_6_odd_1 | P
tx_230400_7_odd_1 | P
tx_230400_8_odd_1 | P
tx_230400_5_no_2 | P
tx_230400_6_no_2 | P
tx_230400_7_no_2 | P
tx_230400_8_no_2 | P
tx_230400_5_even_2 | P
tx_230400_6_even_2 | P
tx_230400_7_even_2 | P
tx_230400_8_even_2 | P
tx_230400_5_odd_2 | P
tx_230400_6_odd_2 | P
tx_230400_7_odd_2 | P
tx_230400_8_odd_2 | P

## receiver_test
Testname | Status | Remark
rx_2400_5_no_1 | P
rx_2400_6_no_1 | P
rx_2400_7_no_1 | P
rx_2400_8_no_1 | P
rx_2400_5_even_1 | P
rx_2400_6_even_1 | P
rx_2400_7_even_1 | P
rx_2400_8_even_1 | P
rx_2400_5_odd_1 | P
rx_2400_6_odd_1 | P
rx_2400_7_odd_1 | P
rx_2400_8_odd_1 | P
rx_2400_5_no_2 | P
rx_2400_6_no_2 | P
rx_2400_7_no_2 | P
rx_2400_8_no_2 | P
rx_2400_5_even_2 | P
rx_2400_6_even_2 | P
rx_2400_7_even_2 | P
rx_2400_8_even_2 | P
rx_2400_5_odd_2 | P
rx_2400_6_odd_2 | P
rx_2400_7_odd_2 | P
rx_2400_8_odd_2 | P
rx_4800_5_no_1 | P
rx_4800_6_no_1 | P
rx_4800_7_no_1 | P
rx_4800_8_no_1 | P
rx_4800_5_even_1 | P
rx_4800_6_even_1 | P
rx_4800_7_even_1 | P
rx_4800_8_even_1 | P
rx_4800_5_odd_1 | P
rx_4800_6_odd_1 | P
rx_4800_7_odd_1 | P
rx_4800_8_odd_1 | P
rx_4800_5_no_2 | P
rx_4800_6_no_2 | P
rx_4800_7_no_2 | P
rx_4800_8_no_2 | P
rx_4800_5_even_2 | P
rx_4800_6_even_2 | P
rx_4800_7_even_2 | P
rx_4800_8_even_2 | P
rx_4800_5_odd_2 | P
rx_4800_6_odd_2 | P
rx_4800_7_odd_2 | P
rx_4800_8_odd_2 | P
rx_9600_5_no_1 | P
rx_9600_6_no_1 | P
rx_9600_7_no_1 | P
rx_9600_8_no_1 | P
rx_9600_5_even_1 | P
rx_9600_6_even_1 | P
rx_9600_7_even_1 | P
rx_9600_8_even_1 | P
rx_9600_5_odd_1 | P
rx_9600_6_odd_1 | P
rx_9600_7_odd_1 | P
rx_9600_8_odd_1 | P
rx_9600_5_no_2 | P
rx_9600_6_no_2 | P
rx_9600_7_no_2 | P
rx_9600_8_no_2 | P
rx_9600_5_even_2 | P
rx_9600_6_even_2 | P
rx_9600_7_even_2 | P
rx_9600_8_even_2 | P
rx_9600_5_odd_2 | P
rx_9600_6_odd_2 | P
rx_9600_7_odd_2 | P
rx_9600_8_odd_2 | P
rx_19200_5_no_1 | P
rx_19200_6_no_1 | P
rx_19200_7_no_1 | P
rx_19200_8_no_1 | P
rx_19200_5_even_1 | P
rx_19200_6_even_1 | P
rx_19200_7_even_1 | P
rx_19200_8_even_1 | P
rx_19200_5_odd_1 | P
rx_19200_6_odd_1 | P
rx_19200_7_odd_1 | P
rx_19200_8_odd_1 | P
rx_19200_5_no_2 | P
rx_19200_6_no_2 | P
rx_19200_7_no_2 | P
rx_19200_8_no_2 | P
rx_19200_5_even_2 | P
rx_19200_6_even_2 | P
rx_19200_7_even_2 | P
rx_19200_8_even_2 | P
rx_19200_5_odd_2 | P
rx_19200_6_odd_2 | P
rx_19200_7_odd_2 | P
rx_19200_8_odd_2 | P
rx_38400_5_no_1 | P
rx_38400_6_no_1 | P
rx_38400_7_no_1 | P
rx_38400_8_no_1 | P
rx_38400_5_even_1 | P
rx_38400_6_even_1 | P
rx_38400_7_even_1 | P
rx_38400_8_even_1 | P
rx_38400_5_odd_1 | P
rx_38400_6_odd_1 | P
rx_38400_7_odd_1 | P
rx_38400_8_odd_1 | P
rx_38400_5_no_2 | P
rx_38400_6_no_2 | P
rx_38400_7_no_2 | P
rx_38400_8_no_2 | P
rx_38400_5_even_2 | P
rx_38400_6_even_2 | P
rx_38400_7_even_2 | P
rx_38400_8_even_2 | P
rx_38400_5_odd_2 | P
rx_38400_6_odd_2 | P
rx_38400_7_odd_2 | P
rx_38400_8_odd_2 | P
rx_76800_5_no_1 | P
rx_76800_6_no_1 | P
rx_76800_7_no_1 | P
rx_76800_8_no_1 | P
rx_76800_5_even_1 | P
rx_76800_6_even_1 | P
rx_76800_7_even_1 | P
rx_76800_8_even_1 | P
rx_76800_5_odd_1 | P
rx_76800_6_odd_1 | P
rx_76800_7_odd_1 | P
rx_76800_8_odd_1 | P
rx_76800_5_no_2 | P
rx_76800_6_no_2 | P
rx_76800_7_no_2 | P
rx_76800_8_no_2 | P
rx_76800_5_even_2 | P
rx_76800_6_even_2 | P
rx_76800_7_even_2 | P
rx_76800_8_even_2 | P
rx_76800_5_odd_2 | P
rx_76800_6_odd_2 | P
rx_76800_7_odd_2 | P
rx_76800_8_odd_2 | P
rx_115200_5_no_1 | P
rx_115200_6_no_1 | P
rx_115200_7_no_1 | P
rx_115200_8_no_1 | P
rx_115200_5_even_1 | P
rx_115200_6_even_1 | P
rx_115200_7_even_1 | P
rx_115200_8_even_1 | P
rx_115200_5_odd_1 | P
rx_115200_6_odd_1 | P
rx_115200_7_odd_1 | P
rx_115200_8_odd_1 | P
rx_115200_5_no_2 | P
rx_115200_6_no_2 | P
rx_115200_7_no_2 | P
rx_115200_8_no_2 | P
rx_115200_5_even_2 | P
rx_115200_6_even_2 | P
rx_115200_7_even_2 | P
rx_115200_8_even_2 | P
rx_115200_5_odd_2 | P
rx_115200_6_odd_2 | P
rx_115200_7_odd_2 | P
rx_115200_8_odd_2 | P
rx_230400_5_no_1 | P
rx_230400_6_no_1 | P
rx_230400_7_no_1 | P
rx_230400_8_no_1 | P
rx_230400_5_even_1 | P
rx_230400_6_even_1 | P
rx_230400_7_even_1 | P
rx_230400_8_even_1 | P
rx_230400_5_odd_1 | P
rx_230400_6_odd_1 | P
rx_230400_7_odd_1 | P
rx_230400_8_odd_1 | P
rx_230400_5_no_2 | P
rx_230400_6_no_2 | P
rx_230400_7_no_2 | P
rx_230400_8_no_2 | P
rx_230400_5_even_2 | P
rx_230400_6_even_2 | P
rx_230400_7_even_2 | P
rx_230400_8_even_2 | P
rx_230400_5_odd_2 | P
rx_230400_6_odd_2 | P
rx_230400_7_odd_2 | P
rx_230400_8_odd_2 | P

## full_duplex_test
Testname | Status | Remark
full_2400_5_no_1 | P
full_2400_6_no_1 | P
full_2400_7_no_1 | P
full_2400_8_no_1 | P
full_2400_5_even_1 | P
full_2400_6_even_1 | P
full_2400_7_even_1 | P
full_2400_8_even_1 | P
full_2400_5_odd_1 | P
full_2400_6_odd_1 | P
full_2400_7_odd_1 | P
full_2400_8_odd_1 | P
full_2400_5_no_2 | P
full_2400_6_no_2 | P
full_2400_7_no_2 | P
full_2400_8_no_2 | P
full_2400_5_even_2 | P
full_2400_6_even_2 | P
full_2400_7_even_2 | P
full_2400_8_even_2 | P
full_2400_5_odd_2 | P
full_2400_6_odd_2 | P
full_2400_7_odd_2 | P
full_2400_8_odd_2 | P
full_4800_5_no_1 | P
full_4800_6_no_1 | P
full_4800_7_no_1 | P
full_4800_8_no_1 | P
full_4800_5_even_1 | P
full_4800_6_even_1 | P
full_4800_7_even_1 | P
full_4800_8_even_1 | P
full_4800_5_odd_1 | P
full_4800_6_odd_1 | P
full_4800_7_odd_1 | P
full_4800_8_odd_1 | P
full_4800_5_no_2 | P
full_4800_6_no_2 | P
full_4800_7_no_2 | P
full_4800_8_no_2 | P
full_4800_5_even_2 | P
full_4800_6_even_2 | P
full_4800_7_even_2 | P
full_4800_8_even_2 | P
full_4800_5_odd_2 | P
full_4800_6_odd_2 | P
full_4800_7_odd_2 | P
full_4800_8_odd_2 | P
full_9600_5_no_1 | P
full_9600_6_no_1 | P
full_9600_7_no_1 | P
full_9600_8_no_1 | P
full_9600_5_even_1 | P
full_9600_6_even_1 | P
full_9600_7_even_1 | P
full_9600_8_even_1 | P
full_9600_5_odd_1 | P
full_9600_6_odd_1 | P
full_9600_7_odd_1 | P
full_9600_8_odd_1 | P
full_9600_5_no_2 | P
full_9600_6_no_2 | P
full_9600_7_no_2 | P
full_9600_8_no_2 | P
full_9600_5_even_2 | P
full_9600_6_even_2 | P
full_9600_7_even_2 | P
full_9600_8_even_2 | P
full_9600_5_odd_2 | P
full_9600_6_odd_2 | P
full_9600_7_odd_2 | P
full_9600_8_odd_2 | P
full_19200_5_no_1 | P
full_19200_6_no_1 | P
full_19200_7_no_1 | P
full_19200_8_no_1 | P
full_19200_5_even_1 | P
full_19200_6_even_1 | P
full_19200_7_even_1 | P
full_19200_8_even_1 | P
full_19200_5_odd_1 | P
full_19200_6_odd_1 | P
full_19200_7_odd_1 | P
full_19200_8_odd_1 | P
full_19200_5_no_2 | P
full_19200_6_no_2 | P
full_19200_7_no_2 | P
full_19200_8_no_2 | P
full_19200_5_even_2 | P
full_19200_6_even_2 | P
full_19200_7_even_2 | P
full_19200_8_even_2 | P
full_19200_5_odd_2 | P
full_19200_6_odd_2 | P
full_19200_7_odd_2 | P
full_19200_8_odd_2 | P
full_38400_5_no_1 | P
full_38400_6_no_1 | P
full_38400_7_no_1 | P
full_38400_8_no_1 | P
full_38400_5_even_1 | P
full_38400_6_even_1 | P
full_38400_7_even_1 | P
full_38400_8_even_1 | P
full_38400_5_odd_1 | P
full_38400_6_odd_1 | P
full_38400_7_odd_1 | P
full_38400_8_odd_1 | P
full_38400_5_no_2 | P
full_38400_6_no_2 | P
full_38400_7_no_2 | P
full_38400_8_no_2 | P
full_38400_5_even_2 | P
full_38400_6_even_2 | P
full_38400_7_even_2 | P
full_38400_8_even_2 | P
full_38400_5_odd_2 | P
full_38400_6_odd_2 | P
full_38400_7_odd_2 | P
full_38400_8_odd_2 | P
full_76800_5_no_1 | P
full_76800_6_no_1 | P
full_76800_7_no_1 | P
full_76800_8_no_1 | P
full_76800_5_even_1 | P
full_76800_6_even_1 | P
full_76800_7_even_1 | P
full_76800_8_even_1 | P
full_76800_5_odd_1 | P
full_76800_6_odd_1 | P
full_76800_7_odd_1 | P
full_76800_8_odd_1 | P
full_76800_5_no_2 | P
full_76800_6_no_2 | P
full_76800_7_no_2 | P
full_76800_8_no_2 | P
full_76800_5_even_2 | P
full_76800_6_even_2 | P
full_76800_7_even_2 | P
full_76800_8_even_2 | P
full_76800_5_odd_2 | P
full_76800_6_odd_2 | P
full_76800_7_odd_2 | P
full_76800_8_odd_2 | P
full_115200_5_no_1 | P
full_115200_6_no_1 | P
full_115200_7_no_1 | P
full_115200_8_no_1 | P
full_115200_5_even_1 | P
full_115200_6_even_1 | P
full_115200_7_even_1 | P
full_115200_8_even_1 | P
full_115200_5_odd_1 | P
full_115200_6_odd_1 | P
full_115200_7_odd_1 | P
full_115200_8_odd_1 | P
full_115200_5_no_2 | P
full_115200_6_no_2 | P
full_115200_7_no_2 | P
full_115200_8_no_2 | P
full_115200_5_even_2 | P
full_115200_6_even_2 | P
full_115200_7_even_2 | P
full_115200_8_even_2 | P
full_115200_5_odd_2 | P
full_115200_6_odd_2 | P
full_115200_7_odd_2 | P
full_115200_8_odd_2 | P
full_230400_5_no_1 | P
full_230400_6_no_1 | P
full_230400_7_no_1 | P
full_230400_8_no_1 | P
full_230400_5_even_1 | P
full_230400_6_even_1 | P
full_230400_7_even_1 | P
full_230400_8_even_1 | P
full_230400_5_odd_1 | P
full_230400_6_odd_1 | P
full_230400_7_odd_1 | P
full_230400_8_odd_1 | P
full_230400_5_no_2 | P
full_230400_6_no_2 | P
full_230400_7_no_2 | P
full_230400_8_no_2 | P
full_230400_5_even_2 | P
full_230400_6_even_2 | P
full_230400_7_even_2 | P
full_230400_8_even_2 | P
full_230400_5_odd_2 | P
full_230400_6_odd_2 | P
full_230400_7_odd_2 | P
full_230400_8_odd_2 | P

## TB_structure
testbench
uart_base_test
env
ahb_agt
scoreboard
uart_reg_block
(regmodel)
uart_agt
sequencer
driver
monitor
sequencer
driver
monitor
adapter
MDR
DLL
DLH
LCR
IER
FSR
TBR
RBR
predictor
functional coverage
adapter
ahb_vif
ahb_vif
uart_vif
uart_vif
UART IP
DUT
AHB interface
UART interface
HSEL = 1
HRESTN = 1
HCLK= 1
Interrupt